## Project Plan
Final Project
Project Lead:
Features and Description | Estimated Implementation | Assigned To | Status
Not Implemented
In Progress
Done
Movement
Basic movement | 1 wk | Alec | Done
Wall jump | 1 wk | Alec | Done
Air jump | 1 wk | Alec | Done
Variable jump | 1 wk | Alec | Done
Combat
Direction based attacks | 2 wk | Alec | Done
Ranged moves | 2 wk | Alec | Done
Multiple Weapons | 2 wk | Alec | In Progress
Object pooling for ranged moves | 2 wk | Alec | Done
Enemies
Ranged Enemies | 2 wk | Nas | In Progress
Enemies that can't attack | 2 wk | Nas | In Progress
Hostile Terrain | 3 wk | Nas | In Progress
Enemy AI | 3 wk | Nas | In Progress
Map
Possible Mini-Map | 1 wk | Nas | In Progress
Research Tile Map | 1 wk | Nas | In Progress
Implement Tile Map | 1 wk | Nas | In Progress
Assets
Research Assets | 1 wk | Allison | In Progress
Implement Assets | 2 wk | Allison | In Progress
Sounds included | 2 wk | Allison | In Progress
Animations
Implement Animation from assets | 3 wk | Allison | In Progress
Insert a row above to add more features to the list.